## Sheet1
TASK ID | TASK NAME | SUBTASK ID | SUBTASK NAME | ESTIMATADE HOURS | ASSIGNED TO | STATUS | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
1 | Project Initiation | 1.1 | Identify stakeholders (teachers, students, administrators) | 4 | Jericho Lapac | Pending
|  | 1.2 | Gather requirements (features, functionalities) | 6 | Jerson Mendoza
|  | 1.3 | Define project scope and limitations. | 8 | ALL
2 | Planning Phase | 2.1 | Create a project timeline with milestones | 3 | Jerson Mendoza | Pending
|  | 2.2 | Allocate resources | 6 | Jericho Lapac
|  | 2.3 | Gather Requirements | 9 | Jericho Lapac
|  | 2.4 | Document Requirements | 11 | Jerson Mendoza
3 | System Design | 3.1 | Create system architecture diagrams (client-server model) | 5 | Jericho Lapac | Pending
|  | 3.2 | Design database schema (tables for students, attendance records | 9 | Jerson Mendoza
|  | 3.3 | Develop wireframes for user interfaces (admin panel, student portal) | 12 | ALL
4 | Development Phase | 4.1 | Set up the development environment (IDE, libraries) | 6 | Jerson Mendoza | Pending
|  | 4.2 | Develop backend (API for attendance management) | 8 | Jerson Mendoza
|  | 4.3 | Develop frontend (user interfaces for students and admins) | 10 | Jericho Lapac
|  | 4.4 | Implement database connections and queries | 15 | ALL
5 | Testing Phase | 5.1 | Conduct unit testing for individual components | 10 | Jericho Lapac | Pending
|  | 5.2 | Perform integration testing to ensure components work together | 20 | Jericho Lapac
|  | 5.3 | Execute user acceptance testing (UAT) with stakeholders | 30 | Jerson Mendoza
|  | 5.4 | Test Cases and Results | 40 | Jerson Mendoza
|  | 5.5 | Bug Reports and Fixes | 60 | ALL
6 | Deployment Phase | 6.1 | Set up the production environment (server configuration) | 9 | Jerson Mendoza | Pending
|  | 6.2 | Deploy the application (upload code, configure database) | 17 | Jerson Mendoza
|  | 6.3 | Train users (students and staff) on how to use the system | 20 | Jericho Lapac
7 | Maintenance and Support | 7.1 | Monitor system performance and user feedback | 40 | Jericho Lapac | Pending
|  | 7.2 | Implement updates and new features based on user needs | 30 | Jerson Mendoza
|  | 7.3 | Provide technical support for users | 50 | ALL